## week 13
Weekly report
Provider : | BRED IT
Drafter : | JULIEN PERUGINI
Drafting date : | 28/3/2018
Period : | from 26/3/2018 to 30/3/2018
Week : | 13
|  | Working Days : 5 | Holiday : 0 | Vacation : 0 | Sick Leave : 0
Project Manager | ANTHONY RATA GOBAL
Project | Tasks | Contributor(s) | Consumed during the period (d/h) | Planned (d/h) | Consumed (d/h) | Remains to be done (d/h) | End date | Palan | % Progress | Comments
10632 - Conseil en investissement PM (activité 63765) | Mantis 0031756: l'affichage des offres (2ème et 3ème projet) vient trop tot et donne celles du projet précédent | JULIEN PERUGINI | [5 empty] | 10632 | 0
| Mantis 0031776: Lorsque l'on veut modifier les produits que l'on a choisit pour un projet, les produits déjà choisis sont supprimés | JULIEN PERUGINI | [5 empty] | 10632 | 0
| Mantis 0031748: Modification de mot | JULIEN PERUGINI | [5 empty] | 10632 | 0
| Mantis 0031678: Anomalie dans rechargement du 2ème projet | JULIEN PERUGINI | [5 empty] | N/A | 0
| Ordonner la liste des objectifs/horizons/risques dans Gestmatricemif | JULIEN PERUGINI ANTHONY RATA GOBAL | [5 empty] | N/A | 0
Test other project | task 1 | Me | 0 | 0 | 0 | 0 |  | 16878 | 100
| task 2 | eff | 0 | 0 | 0 | 0 |  | 64 | 65